## Template
No. | Time | From | To | Inject | Who Delivers | Method of Delivery | Additional Notes/Expected Actions | Capability/Task To Be Addressed
| T - 2 day |  | Controllers, evaluators, and support staff | Controller and Evaluator Training | Lead Controller | In person | Controllers will be trained on how to use the Symptomology Cards and Evaluators on using the EEGs
| T - 1 day |  | Players | Player Training | Drill Planning Team | In person or electronic | Player training will focus on the rules for play and what to expect during the drill
| T - 1 day |  | Actors | Actor Training | Drill Planning Team | In person or electronic | Actors will be trained on how to use the Actor Cards. They can also be briefed on the appropriate dress for the drill and if extra change of clothing is required
| T - 1 day |  | Support staff | Setup and staging of CRC Facility | Drill Planning Team and support staff | In person | The toolkit assumes that the CRC is set up and functional at STARTEX. The operations (not the activation) of the CRC are being drilled and evaluated
Day of Drill
| T - 60 min |  | Controllers, evaluators, and support staff | Controller and evaluator check-in and communications check | Lead Controller and Support Staff | In person | Controllers and Evaluators will check in and be given their assignments, last-minute instructions, and required drill tools (MSEL, ExPlan, EEGs, clipboard, radio, badge, etc.)
| T - 60 min |  | Actors | Actor check-in | Actor Controller | In person | In person
| T - 30 min |  | Players | Player check-in | Support Staff, CRC Director | In person | Players will check in and receive an assignment from the CRC Director. They should report to their area and become familiar with the setup, equipment, forms, etc.
| T - 30 min |  | Media/Observers/VIPs | Media/Observer/VIP Briefing | Observer Controller | In person | VIPs can be briefed separately if desired
| T - 15 min |  | All participants | Final Pre-Drill Briefing, then participants take their stations | Drill Director | In person | Drill Director provides final review of process and administrative instructions (emergency procedures, restrooms, breaks and lunch accommodations, etc.)
STARTEX
1 | T + 0 min |  | All Participants | Scenario Briefing | Lead Controller | In person | Lead Controller reads background scenario
2 | T + 10 min |  | All Players | Staff Briefing | CRC Director | In person | CRC Director gives instructions to CRC staff on preparing for evacuees, including CRC station assignments if not given at check-in | Capability: Implement the elements of the existing local plan for establishing, staffing, equipping, and operating a CRC
3 | T+20 |  | All Players | Players take their stations and report to CRC Director when ready to receive evacuees. |  | In person
4 | T + 25 min | Bus Driver | CRC Director | "This is Pat Evans and I'm driving a bus load of people from the area that was affected by the nuclear bomb. I have (50) people on board and I should be at your facility in less than 5 minutes. There are some people who are not feeling well. Where should I park to offload everyone?" | Controller | Telephone | CRC Director should provide instructions to the bus driver. If specific information about evacuees is requested of the driver, (s)he should stress the need to pay attention to the road and keep call short
5 | unspecified |  | All Players | CRC is declared to be operational | CRC Director | In person | CRC Director declares the CRC to be operational when staffing and resources are reported ready to receive evacuees
6 | T + 30 min |  | Actors | Evacuees arrive at the CRC |  | In person | The first busload of evacuees (actors) arrive at the CRC. Actors will be provided with Actor Cards defining their roles, which may include playing themselves or specific characteristics
· Specific injects chosen by the Drill Planning Team should be inserted below, especially if the inject is time-critical. · For this drill, play will primarily be driven by the Contamination and Actor Cards handed to actors by the Actor Controller. The rate at which the cards with various scenarios are injected should be based on the current activity within the CRC and the expected outcome (e.g., more activity needed for a function or specific evaluation criterion has not been demonstrated).
7
| Time TBD |  |  | ENDEX
| Shortly after EndEx |  | Actors | Actor Debriefing | Actor Controller | In person | Actors should meet to discuss observations
| Shortly after EndEx |  | Players, Controllers, and Evaluators | Hotwash | Lead Controller | In person | Controllers and evaluators should meet to discuss initial observations and recommendations. Players may also share their observations
|  |  | Controllers and evaluators | Controller and evaluator debriefing, complete EEGs | Lead Controller | In person | Controllers and evaluators continue to meet to specifically discuss their input to the After Action Report and complete EEGs (evaluators)
|  |  | Players and support staff, joined later by controllers and evaluators | Site Breakdown/Cleanup | Drill Director | In person