| Dates | Action Items & Notes | Toolkit Resources |
| --- | --- | --- |
| Month/s YEAR 3-4 months before event | - Kick off meeting with core planning team - Identify stakeholders and partners - Draft list of educational resources – use input from partners to update - Determine venue, event date and duration, and name - Develop and initiate communications plan *Distribute save-the-date announcements when event details are confirmed. | - Example soilSHOP Planning Timeline - Example Resources Sheet for Further Information |
| Month/s YEAR 2 months before event | - Develop communication and outreach materials (flyers, logo, announcements, soil sampling kit) - Continue meetings and calls with stakeholders/planning team - Review supplies and equipment needs (XRFs, gloves, calculators, log books, forms; tables, chairs, pop up tents) - Discuss logistics – venue, AC outlets, parking, restrooms, rain plan, etc. - Address translation (if needed) - are community volunteers available? - Identify potential personnel for event (volunteers, agency staff, etc.) *Note any upcoming vacations for key personnel | - Soil Sampling Cartoon - Color - soilSHOP Logo (writable pdf) - Log In Form - Example Outreach Flyer - Example soilSHOP Equipment and Printed Materials Checklist - Example Staff Roles and Functions |
| Month/s YEAR 1 month before | - Confirm personnel commitments from various agencies/volunteers - Assign staff to station teams (Log In, Screening, Health Ed.) and schedule team calls - Implement communications plan (through web sites, list serves, newsletters, local papers, businesses, community meetings, etc.) - Finalize all event materials (Log In Form, Labels, Sample Result Card, Health Education Consultation Evaluation Form, signage, Etc.) - Hold group call to finalize sample kit distribution plan | - Health Education Consultation Evaluation Form - Example soilSHOP Sample Labels - Example Screening Result Card - Example Staff Roles and Functions - Example soilSHOP Equipment and Printed Materials Checklist |
| Month/s YEAR 3-4 weeks before | - Schedule team calls – Log In/Registration Team, Screening Team, and Health Education Team – and schedule training calls - Continue implementing communications plan (Round 1 of Sample Kit Distribution) - Continue logistics planning - Finalize educational materials (Resources Sheet, Trifold, etc); print materials as needed or post on a community/event web site - Review equipment and printed materials checklist; order any materials/supplies needed | - soilSHOP_Trifold – Eng/Span - Example Resources Sheet for Further Information - Example soilSHOP Equipment and Printed Materials Checklist |
| Month/s YEAR 2-3 weeks before | - Continue outreach meetings in community - Continue logistics planning - Confirm availability of all materials/supplies - Develop soil screening plans (Example Soil Screening Guidance) - Finalize health educator materials; reach agreement with partners on key messages - Discuss health, safety and other special considerations | - Example soilSHOP Equipment and Printed Materials Checklist - Example Soil Screening Guidance |
| Month/s YEAR 1-2 weeks before | - Continue logistics planning - Visit event venue to review logistics - Confirm staff assignments and availability - Conduct volunteer and staff training calls - Continue implementing communications plan (Round 2 of Sample Kit Distribution)Print and ship or package all event material *Note: Keep track of holidays impacting business hours and shipping capabilities | - Example Staff Roles and Functions |
| 2-3 days before | - Develop and share cell phone contact list for event team - Send logistics email to event team with directions, contact list, weather forecast, dress code, food, parking, and other necessary information |  |
| Day of soilSHOP: [DAY], [MONTH] [DAY], [YEAR] - Implement soilSHOP (arrive early for set up!) |  |  |
| 1 - 2 weeks Post-Event | - Conduct post-event call with soilSHOP staff and partners to review event successes and lessons learned - Send recap email and thank you letters to staff and partners - Share event information with soilSHOP@cdc.gov – visit [www.(insert future soilSHOP website, past events page url).com] | - Example Thank You Letter |

= Core planning group activities			= Core planning group, soilSHOP partners, and staff activities