## ProjectPlanTemplate
ID | Task | Start Date | End Date | Predecessor Tasks | Task Owner | Resource Names
1 | State Medicaid Agency ICD-10 Implementation | 2010-09-01 08:30 | 2014-03-30 08:30
2 | Critical Dependencies | 2011-01-01 17:00 | 2011-01-01 17:00
3 | Track 5010 (Compliance Date: January 1, 2012) | 2011-01-01 17:00 | 2011-01-01 17:00
4 | Milestone: Start Program | 2010-09-01 08:30 | 2010-09-01 08:30
5 | Awareness | 2010-09-01 08:30 | 2014-03-14 08:30
6 | Internal Awareness, Communication, and Education/Training | 2010-09-01 08:30 | 2014-03-14 08:30
7 | Provide Awareness Training to ICD-10 Leadership and ICD-10 Team | 2010-09-01 08:30 | 2010-11-30 08:30 | 4
8 | Educate and Train Staff (including training during transition and implementation) | 2010-11-30 08:30 | 2014-03-14 08:30 | 7
9 | External Awareness, Communications, and Outreach | 2010-11-30 08:30 | 2014-03-14 08:30
10 | Conduct Communications with State Entities/Trading Partners/Providers/Contractors/Vendors | 2010-11-30 08:30 | 2014-03-14 08:30 | 7
11 | Monitor Trading Partner ICD-10 Transition Status | 2010-12-30 08:30 | 2014-03-14 08:30 | 25
12 | Identify and Leverage Partnering/Outreach Opportunities (with providers, advisory boards, etc.) | 2010-11-30 08:30 | 2014-03-14 08:30 | 7
14 | Assessment | 2010-09-01 08:30 | 2011-05-29 08:30
15 | High-level planning for ICD-10 activities | 2010-09-01 08:30 | 2010-10-31 08:30
15 | Establish an Executive Sponsorship, ICD-10 Steering Committee, ICD-10 Point of Contact | 2010-09-01 08:30 | 2010-10-01 08:30 | 4
16 | Establish and Organize Impact Assessment Team | 2010-09-01 08:30 | 2010-10-01 08:30 | 15SS
17 | Review/Establish Program Management Office and Governance Structure | 2010-10-01 08:30 | 2010-10-31 08:30 | 15
18 | Develop Tools/Processes to Facilitate Assessment Activities | 2010-09-01 08:30 | 2010-11-30 08:30 | 15SS,16SS
19 | Perform Impact Assessment | 2010-10-01 08:30 | 2010-12-30 08:30
20 | Identify Policies Impacted by ICD-10 | 2010-10-01 08:30 | 2010-12-30 08:30 | 16
21 | Identify Processes Impacted by ICD-10 | 2010-10-01 08:30 | 2010-12-30 08:30 | 16
22 | Identify Systems Impacted by ICD-10 | 2010-10-01 08:30 | 2010-12-30 08:30 | 16
23 | Identify Impacts of ICD-10 on Trading Partners/Providers/Contractors/Vendors Relations | 2010-10-01 08:30 | 2010-12-30 08:30 | 16
24 | Document and Communicate Impact Assessment Findings | 2010-11-30 08:30 | 2010-12-30 08:30 | 23SS+2 emons
25 | Milestone: Impact Assessment Completed | 2010-12-30 08:30 | 2010-12-30 08:30 | 24,20,21,22,23
26 | Determine Administrative Budget for DDI and O&M | 2010-11-30 08:30 | 2010-12-30 08:30 | 24SS
27 | Develop Remediation Strategy/Plan | 2010-12-30 08:30 | 2011-05-29 08:30
28 | Create and Receive Approval of Remediation Strategy for Policies, Processes, and Systems (including Cross-Walking and Mapping Strategies) | 2010-12-30 08:30 | 2011-03-30 08:30 | 26
29 | Create End-to-End Testing Strategy | 2011-02-28 08:30 | 2011-03-30 08:30 | 28SS+2 emons
30 | Milestone: Core ICD-10 Strategies Developed | 2011-03-30 08:30 | 2011-03-30 08:30 | 29,28
31 | Develop Financial Plans | 2011-02-28 08:30 | 2011-05-29 08:30
32 | Forecast Claims Payments with ICD-10 Codes | 2011-02-28 08:30 | 2011-03-30 08:30 | 28SS+2 emons
33 | Develop and Execute Resource Acquisition Plan | 2011-02-28 08:30 | 2011-05-29 08:30 | 28SS+2 emons
34 | Develop Advanced Planning Documents (APDs), and Coordinate APD Approvals | 2011-02-28 08:30 | 2011-05-29 08:30 | 28SS+2 emons
35 | Establish and Organize Remediation Team | 2011-02-28 08:30 | 2011-03-30 08:30 | 30SS-1 emon
36 | Develop Detailed Implementation Plans | 2011-03-30 08:30 | 2011-05-29 08:30 | 35
37 | Remediation | 2011-05-29 08:30 | 2012-05-23 08:30
38 | Develop Updates to Policies | 2011-05-29 08:30 | 2011-08-27 08:30 | 34SS+3 emons
39 | Develop Updates to Processes | 2011-05-29 08:30 | 2011-08-27 08:30 | 34SS+3 emons
40 | IT Changes | 2011-05-29 08:30 | 2012-05-23 08:30
41 | Develop System Requirements and Change Requests | 2011-05-29 08:30 | 2011-08-27 08:30 | 34SS+3 emons
42 | Design System Changes | 2011-08-27 08:30 | 2011-10-26 08:30 | 41
43 | Develop System Changes | 2011-10-26 08:30 | 2012-04-23 08:30 | 42
44 | Perform System Tests for Each System | 2012-03-24 08:30 | 2012-05-23 08:30 | 43SS+5 emons
45 | Milestone: ICD-10 Changes Completed | 2012-05-23 08:30 | 2012-05-23 08:30 | 38,39,41,42,43,44
46 | End-to-End Testing | 2012-02-23 08:30 | 2013-07-02 08:30
47 | Develop Test Plans and Test Data | 2012-02-23 08:30 | 2012-04-23 08:30 | 43SS+4 emons
48 | Test Internally: End-to-End - Level I Testing | 2012-04-23 08:30 | 2012-10-20 08:30 | 47
49 | Test Externally: Partner End-to-End - Level II Testing | 2012-10-05 08:30 | 2013-07-02 08:30 | 48SS+5.5 emons
50 | Milestone: End-to-End Testing of ICD-10 Completed | 2013-07-02 08:30 | 2013-07-02 08:30 | 47,48,49
51 | Transition | 2013-04-04 08:30 | 2014-03-30 08:30
52 | Publish Final Rule and Sub-regulatory Policy Updates | 2013-04-04 08:30 | 2013-10-01 08:30 | 55FS-6 emons
53 | Publish Final Rule and Sub-regulatory Process Updates | 2013-04-04 08:30 | 2013-10-01 08:30 | 55FS-6 emons
54 | Transition and Implement System Changes | 2013-07-03 08:30 | 2013-10-01 08:30 | 49,52SS+3 emons,53SS+3 emons
55 | Milestone: ICD-10 Implemented and Live | 2013-10-01 08:30 | 2013-10-01 08:30
56 | Post Transition Support | 2013-07-03 08:30 | 2014-03-30 08:30
57 | Provide Customer Support | 2013-07-03 08:30 | 2013-12-30 08:30 | 54SS
58 | Monitor Operations | 2013-07-03 08:30 | 2014-03-30 08:30 | 54SS